## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 5/11/21 to 5/17/21 | 1. Held two (2) 1 hour meetings to discuss overall project and task assignments. 2. Decided on project: Calorie Tracker App. 3. Developed week 1 / iteration 0 docs - SPPP, Progress Report, etc. | 1. Not all members familiar with Flask. 2. Hosting platform. | 1. Time zones for members - communication limited to certain blocks of time to faciliate all members participation. | 1. Conduct 2 stand-up meetings per week to ensure that all tasks are on track. 2. Encourage regular use of Slack channel. 3. Keep pivatol tracker requirements up-to-date. | [6 empty] | 67.5 | 16 | 23 | 4 | 5.5 | 0 | 3 | 3.5 | 5.5 | 10
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ray Clark | review and edit requirements and overall description of the app | Made revisions and additions to the requirements section. | Began giving thought to overall system design.
Josephine But
Danny Graziano
Chen Zhao
Huimin Diao
Zixia Zhou

## yuting
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Josephine But
Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-5/17 | 17.5 | 14.5 | 3 | 0 - learn git and Flask, read several tutorials 4 - Wrote the QA Analyst Plan 5 - Chat for the project requirement and wrote the meeting minute 6 - set up git 7 - research on project ideas, testing tools, testing matrix, defect management | 5 | 0 |  |  | 3 | 1 | 0.5 | 5 | 1. Finish QA Analyst Plan and Monitory and Controlling Tools and Mechanisms sections of SPPP 2. Set up git, commit a test message on git, finish lab1. 3. Wrote Meeting Minute report |  |  | 0 - continue to learn Flask 1 - to define requirements 3 - implement a a simple application with Flask 6 - Set up Selenium | 6

## Huimin Diao
Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-05/16 | 15 | 4 | 2 | 0 - learn git and familiar with Github 6 - set up git 7 - research similar products | 2 | [5 empty] | 1 | 3 | 1. Set lab1 git, then merge and delete it 2. write readme file for iteration 0 3. find similar productions |  |  | 15 | 13

## Chen Zhao
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05.11 -- 05.18 | 20 | 20 | 3 | 0--Learning things about git, pivotal tracker, agile development 1--Think about user requirement in project 2--Design what we will do, the goal of our project and basic and advanced function 5--Chat in Slack 6--set git | 5 | 2 | 2 |  |  | 0.5 | 1 |  | 1. Provide the project body and general ideas 2. Provide some primary requirement 3. Provide a simple video of using pivotaltracker 4. Write 2 sections of SPPP | 1. Not familiar with requirement analysis, and having some different ideas with team members. 2. Communication with team members is not very smooth. 3. Time zone difference make me always have meeting in 23:00. | 1. Keep learning, especially class in week 2 is about requirement. 2. More commnication, if listening and speaking is not good, try more written communication. 3. Control meeting time. | 0--Learning about Requirement Analysis and SE 1--Do update of our project's requirement 2--Discussion with team about where should change and update about project requirement | 14

## Danny Graziano
Lead Roles: Design & Implementation leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-5/17 | 6 | 4 | 2 | 0 - read flask documentation, FDA API docs and example in Postman 1 - 2 - mock up plan w/ Chen? 3 - 4 - 5 - Write Objectives & priorities, risk management in SPPP, meet with sub-group to divide tasks 6 - set up repo for lab0 locally, IDE setup and local python env (environment.yml?) 7 - | 3 |  | 0.5 |  |  | 1.5 | 1 |  |  |  |  | 0 - Learn Flask (specifically user management) 1 -Fully define design requirements with team 2 - Design Mock up drawing with design subteam 3 - implement a mock user login portal | 10

## Ray Clark
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 5/11/21 to 5/17/21 | 20 | 20 | 3 | 0 - learn git & github, read tutorial on git, pivitol tracker, etc. 1 - define high level requirements for Calorie Tracker app 2 - Outline general design on Zoom calls, assgn general responsibilities. 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 5 | 2 | 3 | 0 | 0 | 0.5 | 1 | 1 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. edit various other docs for iteration 0 | 1. not familar with Flask framework, need to learn. 2. communication is not clear. Task assignments is not clear. 3. Difficult setting up meetings with various time zones. | 1. Work on Flask tutorial over next 2 weeks, be able to create simple Flask app next week 2. Communicate regularly with all team members, hold 2 stand up meetings per week. 3. Send task assignments to all members | 0 - continue to learn Flask 1 - continue to define requirements 3 - implement a basic hello world on Flask | 12.5

## Zixia Zhou
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11/2021 to 05/17/2021 | 8 | 5 | 3 | 0-learn git and flask 6-set up git 7-write configuration managment plan | 3 | [5 empty] | 1 | 1 | -finish configuration management plan -Set up git -Participate in Iteration 0 presentation |  |  | -learn more flask -continue to define requirements | 5