## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*3*4=48 | team leader and all members | 2020-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
add new team members
Lack of motivation or responsibility
Communication | duplicate work
worked on wrong components
useless work
inconsistent work
Requirements | unclear requirements
scope creep
constant requirements changes
Management | improper task assignments
improper planning
lack of management skills
Technology competence | Not familiar with the framework used
Not familiar with the programming language used
Not familiar with unit testing
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design
improper technology stack
Messy code
Testing | Not enough testing
Integration and deployment | Not enough time for integration and deployment
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.