## Summary-GroupIterationProgress
iteration # | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 5/11/21 to 5/17/21 | 1. Held several 1 hour meetings to discuss overall project and task assignments. 2. Decided on project: Calorie Tracker App. 3. Developed week 1 / iteration 0 docs - SPPP, Progress Report, etc. 4. Developed week 2 / iteration 1 docs - SPPP, Progress Report, etc. | 1. Not all members familiar with Flask. 2. Hosting platform. | 1. Time zones for members - communication limited to certain blocks of time to faciliate all members participation. | 1. Conduct 2 stand-up meetings per week to ensure that all tasks are on track. 2. Encourage regular use of Slack channel. 3. Keep pivatol tracker requirements up-to-date. | [6 empty] | 67.5 | 16 | 23 | 4 | 5.5 | 0 | 3 | 3.5 | 5.5 | 10
1 | 5/18/21 to 5/31/21 | 1. Held three (3) 1-hour meetings to discuss overall project and task assignments. 2. Decided on paired programming teams and assigned specific coding tasks to those teams. 3. Continued work on week 2 / iteration 1 docs - SPPP, SDD, Progress Report, Risk Spreadsheet, and presentation. | 1. Had discussion regarding selection of database and decided on sqlite. 2. Only 1 team member has experience with Flask--other members will lean this technology. 3. Discussion re: Hosting platform--decided that local host is easiest and satisfactory for the project. 4. API for USDA calorie data may not supply all info. needed. 5. Implemented code for reg/login process and to access USDA API data. 6. Began coding UIs in HTML. | 1. Time zones for members still an issue - communication limited to certain blocks of time to faciliate all members participation. 2. Switched to AM in CST and PM in PST to accomodate all members. 3. Coninued use of Slack for group comunications. | 1. Now Conducting 2 stand-up meetings per week (Wed. following lec., Fri or Sunday) to ensure that all tasks are on track and group submission will be complete. 2. All members using Slack regularly. 3. Keep pivatol tracker requirements up-to-date. | 3 | [5 empty] | 91 | 15 | 29 | 5.5 | 7 | 16 | 0.5 | 6.5 | 5.5 | 23

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Ray Clark | review and edit requirements and overall description of the app | Make revisions and additions to the requirements section on PT | Overall system design, master class diagram and user flow diagram. |  | Participate in both PPT and Video presentations | Assist with code for reg/login |  |  | create agenda, schedule and manage group Zoom calls.
Josephine But
Danny Graziano | Objectives, overall document review, presentation recording |  | Software architecture, classes & methods
Chen Zhao
Huimin Diao
Zixia Zhou

## yuting
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Josephine But
Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-5/17 | 17.5 | 14.5 | 3 | 0 - learn git and Flask, read several tutorials 4 - Wrote the QA Analyst Plan 5 - Chat for the project requirement and wrote the meeting minute 6 - set up git 7 - research on project ideas, testing tools, testing matrix, defect management | 5 | 0 |  |  | 3 | 1 | 0.5 | 5 | 1. Finish QA Analyst Plan and Monitory and Controlling Tools and Mechanisms sections of SPPP 2. Set up git, commit a test message on git, finish lab1. 3. Wrote Meeting Minute report |  |  | 0 - continue to learn Flask 1 - to define requirements 3 - implement a a simple application with Flask 6 - Set up Selenium | 6
2 | 05/18-05/25 | 28 | 26 | 2 | 0 - learn git and Flask, read several tutorials 1 - create user stories 3 - develop Registration and Login features, create database and table. 4 - Add the Acceptance test section to QA Analyst Plan 5 - Chat for the project requirement and subgroup meeting 7 - research on security of API keys, write Flask App, using different database to connect with Flask, different kinds of password hashing. | 6 | 0.5 |  | 9 | 0.5 | 1 |  | 9 | 1. Add an function acceptance testing section to the QA Analyst Plan. 2. Developed Registration and Login features. 3. Create database and table. 4. Create an Iteration 1 presentation template. 5. Create User Stories for Registration and Login 6. Provide reference for storing API Keys. |  |  | 0 - continue to learn Flask 4 - write the testing report 3 - write the unit tests for Registration and Login. 4 - Tests for Registration and Login. 2 - write the UI Design in SDD document. 7 - write the presentation (for some sections). 7 Make a presentation video with Ray. 8 Set up Selenium | 20
3 | 05/26-06/01 | 14 | 11 | 3 | 0 -learn git and Flask, Pyunit and Pytest, read several tutorials 1 - Review and create User Stories. 2 - Create mock up UI for Landing page, About, Registration, Login, User's dashboard and Create A Meal/ Calculate Calories and User profile pages. 3 - develop Registration and Login features. 5 chat for the project requirement and subgroup meeting 7 - Wrote the SDD- UI Section, presentation powerpoint(Registration and Login) section, create video presentation, Create Registration/Login code walk through video | 6 | 0.3 | 0.6 | 0.6 |  | 0.5 |  | 3 | 1. Developed Registration and Login features. Submitted it to the github. 2. Wrote the SDD-UI Section. 3. Create Registration/Login code walk through video. 4. Review and create User Stories. 5. Update the SPPP document ( QA Section). 6. Create the power point template. 7. Update the presentation power point. 8. Create the video presentation with Ray. 9. Create mock up UI for Landing page, About, Registration, Login, User's dashboard and Create A Meal/ Calculate Calories and User profile pages. |  |  | 0 - continue to learn flask, pyunit and pytest. 3 - write the unit tests for Registration and Login. 4 - Test for Registration and Login Features. 7 - Set up Selenium. write two tests with Selenium. | 15

## Chen Zhao
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05.11 -- 05.18 | 20 | 20 | 3 | 0--Learning things about git, pivotal tracker, agile development 1--Think about user requirement in project 2--Design what we will do, the goal of our project and basic and advanced function 5--Chat in Slack 6--set git | 5 | 2 | 2 |  |  | 0.5 | 1 |  | 1. Provide the project body and general ideas 2. Provide some primary requirement 3. Provide a simple video of using pivotaltracker 4. Write 2 sections of SPPP | 1. Not familiar with requirement analysis, and having some different ideas with team members. 2. Communication with team members is not very smooth. 3. Time zone difference make me always have meeting in 23:00. | 1. Keep learning, especially class in week 2 is about requirement. 2. More commnication, if listening and speaking is not good, try more written communication. 3. Control meeting time. | 0--Learning about Requirement Analysis and SE 1--Do update of our project's requirement 2--Discussion with team about where should change and update about project requirement | 14
2 | 05.18 -- 05.25 | 12 | 12 | 2 | 0--Learning Flask 1--Update requirement to make it more professional and detailed 5--Having meeting and do meetingmintue one time | 4 | 2 |  |  |  | 1 |  |  |  | 1. Not familiar with Flask and API, while I want to contribute part of code, so that I really need more time to learn Flask and write some code 2. Not familar with API 3. Not familar with test 4. Listening is not good, there are a little difficult for me to communicate with team mebmer online... | 1. Keep learning Flask 2. Need learning some knowledge of test | 0--Learning about Flask and test 2--Discussion with team | 7
3 | 05.25 -- 06.01 | 16 | 16 | 3 | 0--Learning Flask, front end 1--Discuss in the group meeting, and make sure the process of requirement. And I manage those requirement in pivotaltracker. 2--Discuss and design the UI togeter. 3--Make some page with html and css to impliment the UI. 5--Meeting with group and subgroup. | 4 | 1 | 1 | 3 |  | 2 |  |  |  | 1. At first I am going to do backend with flask, while after some dicussion I will mainly do front end coding work. 2. New meeting time is very good for me! Which is a good thing. 3. Not familar with css... 4. I am not sure how to make our project be a whole. | 1. Learning frontend knowledge. 2. Learning some software knowledge. | 0--Learning about frontend. 2--Discussion with team. | 11

## Huimin Diao
Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-05/16 | 15 | 4 | 2 | 0 - learn git and familiar with Github 6 - set up git 7 - research similar products | 2 | [5 empty] | 1 | 3 | 1. Set lab1 git, then merge and delete it 2. write readme file for iteration 0 3. find similar productions |  |  | 15 | 13
2 | 05.18 -- 05.25 | 18 | 10 | 2 | 0 - Learning Flask and Github 1 - create user stories 5 - Group meeting 7 - Learn build UI and cooperate with Zixia | 5 | 2 |  |  |  | 1 |  | 8 | 1. Modify readme file in Github 2. Build interface in project(not done yet) 3. design algorithm in project |  |  | 1. Keep learning Flask and Github 2. Learn more about Interface part | 15
3 | 05/26-06/01 | 22 | 20 | 2 | 0 - learing flask, github, JS 2 - design project interface UI 5 - teammate meeting and wirte meeting minutes | 1 |  | 18 |  |  | 2 |  |  | 1. readme file 2. meeting minutes 3. Web UI 4. key algorithms in SDD 5. iteration relase | not familiar with JS |  | 20 | 22

## Danny Graziano
Lead Roles: Design & Implementation leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11-5/17 | 6 | 4 | 2 | 0 - read flask documentation, FDA API docs and example in Postman 1 - 2 - mock up plan w/ Chen? 3 - 4 - 5 - Write Objectives & priorities, risk management in SPPP, meet with sub-group to divide tasks 6 - set up repo for lab0 locally, IDE setup and local python env (environment.yml?) 7 - | 3 |  | 0.5 |  |  | 1.5 | 1 |  |  |  |  | 0 - Learn Flask (specifically user management) 1 -Fully define design requirements with team 2 - Design Mock up drawing with design subteam 3 - implement a mock user login portal | 10
2 | 5/18-5/25 | 14 | 10 | 4 | 0 - continue learning flask with examples 2 - data fetch queries, API key handling 3 - functions written to gather data from USDA and add to our internal database 5 - help coordinate database schema decisions 6 - configure project environment.yml, IDE integration, projectroot and general project structure | 3 |  | 5 | 3 |  | 0.5 | 3.5 |  | callback functions for retrieving USDA data project envioronment config | SQL database integration w data | coordination w/ login and user team to integrate this feature into existing user db | 0 - learn project env path setup schemes, sql anonymous functions to retrieve data 2 - mock up revisions w/ Ray 3 - timestamping for user entries in database 4 - tests for USDA api calling functions 5 - clarify testing strategy 6 - trim down environment, too many un-necessary packages! | 15
3 | 5/26-6/1 | 15 | 11 | 4 | 0 - learn sqlite3 setup and sample schemas & queries 2 - design schema and queries for storing fetched data internally 3 - backend calls to our internal DB and USDA written and ready for integration with frontend 5 - planning meetings 6 - switch project to requirements.txt from conda, recreate python environment, fix incorrect versions | 3 |  | 4 | 4 |  | 2 | 2 |  | USDA data storage in internal database | database only setup for storage of food objects, we need a way to track meals as well | begin mockup link with frontend edit db schema for meals | 0 - learn testing suite software 2 - Wireframe work from rough sketch 3 - frontend connections for db and search calls 4 - tests for USDA api calling functions 5 - clarify testing strategy 6 - initiate pull requests for features back into develop, create new branches for test development | 20

## Ray Clark
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 5/11/21 to 5/17/21 | 20 | 20 | 3 | 0 - learn git & github, read tutorial on git, pivitol tracker, etc. 1 - define high level requirements for Calorie Tracker app 2 - Outline general design on Zoom calls, assgn general responsibilities. 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 5 | 2 | 3 | 0 | 0 | 0.5 | 1 | 1 | 1. Write 3 sections of SPPP 2. Started work on SDD doc. 3. Held meeting to discuss the overall presentation 4. began edits of various other docs for iteration 1 | 1. not familar with Flask framework, need to learn. 2. communication is not clear. Task assignments is not clear. 3. Difficult setting up meetings with various time zones. | 1. Work on Flask tutorial over next 2 weeks, be able to create simple Flask app next week 2. Communicate regularly with all team members, hold 2 stand up meetings per week. 3. Send task assignments to all members | 0 - continue to learn Flask 1 - continue to define requirements 3 - implement a basic hello world on Flask | 12.5
2 | 5/18/21 to 5/24/21 | 20 | 20 | 3 | 0 - Continue learning Git GitHub, pivitol tracker overview, 2 tutorials on Flask & 1 tutorial on Sqlite 1 - Expand requirements for Calorie Tracker app 2 - Outline general design on Zoom calls, assgn general responsibilities for coding different sections and for production of the Iteration 1 docs. 3. Implementation - held meeting with Jos to discuss coding of reg/login, began coding in Flask/Python. 5 - Revise the project plan, send reminders to team members 6 - Environment Config - Set up VS Code, install Flask, Install Sqlite 7 - Continue research of similar products, took screen shots of UIs of similar products. | 6 | 1 | 2 | 4 | 0 | 1 | 2 | 1 | 1. Expanding on sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4. edit various other docs for iteration 0 | 1. Not familar with Flask framework, not familiar with Sqlite different tutorials but had trouble configuring virtual env. 2.Task assignments need better definition. 3. Difficult setting up meetings with various time zones. | 1. Worked on Flask tutorials, worked on sqlite tutorials. 2. Communicate regularly with all team members, hold 2 stand up meetings per week via Zoom. 3. Send task assignments to all members | 0 - continue to learn Flask & Sqlite 1 - continue to define/refine requirements & tasks 3 - Continue coding the reg/login pages and push to GitHub when complete. | 17
3 | 5/25/21 t0 5/31/21 | 20 | 20 | 3 | 0 - Continue work with pivitol tracker, addt'l tutorials on Flask- Expand requirements for Calorie Tracker app 1 - Discussed features/requirements on 5/26 call, refined requirements on PT. 2 - Outline general design on Zoom calls, further discussion on coding sections and production of Iteration 1 docs, worked on master class diagram and user flow. 3. Implementation - team completed code to access to USDA API data, reg/login and some mock-up of home page, etc, in HTML. 5. Communication - Continued use of Zoom meetings and regular correspondence using Slack. 6 - Environment Config - Using virtual env for Flask implementation and SQLite for DB. 7 - Continue research of similar products, took screen shots of UIs of similar products and discussed at Zoom meeting. | 3 | 2 | 4 | 1 | 0 | 1 | 1 | 1 | 1. Expanding on sections of SPPP 2. Organized Zoom calls and agenda 3. Participate in Iteration 1 presentation 4. refined/revised requirements on PT 5. Edit SPPP & SDD and preapre PPT presentation for Iteration 1 | 1. Working through wireframing using Balsamic - no previous experience with this platform. ferent tutorials but had trouble configuring virtual env. 2. Task assignments need better definition. 3. Difficult setting up meetings with various time zones. | 1. Worked tutorial for Balsamic. 2. Communicate regularly with all team members, hold 2 stand-up meetings per week via Zoom and regular comm on Slack. 3. Discussed tasks using agenda on Zoom meetings. | 0 - Complete Balsamic tutorial and start wireframes of UI pages. 1 - continue to define/refine requirements & tasks 3 - Continue coding the bckend and UIs | 13

## Zixia Zhou
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/11/2021 to 05/17/2021 | 8 | 5 | 3 | 0-learn git and flask 6-set up git 7-write configuration managment plan | 3 | [5 empty] | 1 | 1 | -finish configuration management plan -Set up git -Participate in Iteration 0 presentation |  |  | -learn more flask -continue to define requirements | 5
2 | 05/18/2021 to 05/25/2021 | 15 | 13 | 2 | 0-learn flask 5-group meeting about Iteration1 7-finish lab2 and Quiz1 | 5 |  |  |  |  | 2 |  | 5 | -learn more flask -review module 1 &2 -create user stories on pivotaltracker |  |  | -learn more flask -finish iteration1 | 13
3 | 05/26/2021 to 06/01/2021 | 7 | 5 | 2 | 0-learn flask 5-group meeting about Iteration1 and update the SDD document 7-write Security Design of SDD | 3 | [5 empty] | 1 | 1 | -Decided on the security design section with the group during team discussions and wrote the security design of the SDD |  |  | -Learned the hash encryption algorithm | 5