## Risks
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personnel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*3*4=48 | team leader and all members | 2020-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
Personnel | add new team members | The addition of new team members will require time to educate those members on the current status of the project | 1 | 3 | 3 | 45 | team leader and all members | N/A | Assign tasks to new members | No new members have been added and none are expected | Open
Personnel | Lack of motivation or responsibility | One or more team members may not be omotivated to complete tasks | 1 | 3 | 3 | 45 | team leader and all members | N/A | Talk with team member | No members have exhibited this problem | Open
Communication | duplicate work | More than 1 member inadvertantly works on same task, thereby duplicating work. | 1 | 3 | 2 | 30 | team leader and all members | N/A | Make certain to have regular meetings to ensure all members know their tasks. | No duplicate work at this stage | Open
Communication | worked on wrong components | More than 1 member inadvertantly works on the wrong task. | 1 | 3 | 2 | 30 | team leader and all members | N/A | Make certain to have regular meetings to ensure all members know their tasks. | This has not been a problem | Open
Communication | useless work | A member works on a task that later proves to be useless. | 2 | 2 | 2 | 32 | team leader and all members | N/A | Make certain to have regular meetings to ensure all members know their tasks. | This has not been a problem | Open
Communication | inconsistent work
Requirements | unclear requirements | Requirements are not clearly stated | 2 | 5 | 5 | 20 | team leader and all members | N/A | Make certain to have regular meetings to ensure that all reqs are well defined and understood. Update PTracker regularly. | This has not been a problem | Open
Requirements | scope creep | The definition of scope creep is when a project’s scope changes, the project work starts to extend, or “creep”, beyond what was originally agreed. | 2 | 2 | 2 | 32 | team leader and all members | N/A | Make certain to have regular meetings to ensure that all reqs are well defined and understood. Update PTracker regularly. | This has not been a problem | Open
Management | improper task assignments | Task are assigned to member without the required capability. | 2 | 3 | 3 | 36 | team leader and all members | N/A | Make certain to have regular meetings to ensure all members are assigned task for which they are capable. | This has not been a problem | Open
Management | improper planning
Management | lack of management skills
Technology competence | Not familiar with the framework used | Members of the team are unfamilia with a key technologyor framework | 4 | 5 | 4 | 8 | team leader and all members |  | Make certain that members are assigned tasks for which they are capable. Encourage all members to learn the key techs. | Several members have learned Flash using online tutorials | Open
| Not familiar with the programming language used | Members of the team are unfamiliar with a key languages used. | 4 | 5 | 4 | 8 | team leader and all members |  | Make certain that members are assigned tasks for which they are capable. Encourage all members to learn the key techs. | All members know the primary language which is Pyton | Open
Not familiar with unit testing
Other technology incompetence
| Not familiar with Git | Members of the team are unfamiliar with Git and GitHub. | 2 | 3 | 3 | 36 | team leader and all members |  | Encourage all members to learn the key techs. | All members had to learn Git & GitHub for Lab 1. | Open
Design and implementation | Improper design
improper technology stack
| Messy code | Code is written in a por fashion and is not properly commented. | 2 | 2 | 4 | 64 | team leader and all members |  | Encourage all members to learn the key techs. | All members had to learn Git & GitHub for Lab 1. | Open
Testing | Not enough testing | Code is inadequately tested | 3 | 4 | 5 | 30 | team leader and all members |  | Make certain their is a good test plan in place. | Review tet plan and make certain that all features are properly tested. | Open
Integration and deployment | Not enough time for integration and deployment | Application is too ambitious and requires more time than is available | 1 | 3 | 4 | 60 | team leader and all members |  | Make certain their is a good test plan in place. | Review tet plan and make certain that all features are properly tested. | Open